## Iteration Estimated Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Omer | Ruby | Thomas | Sandy | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
[5 empty] | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Requirements |  |  |  |  | 4 |  | 244
|  | Research business | Requirements Analyst | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Gather information (questionnaire) | Requirements Analyst | All | 1 |  | 2 |  | 2 | 2 | 2 | 2 | 8
|  | Analyze business needs | Requirements Analyst | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Gain access to current website (Wordpress) |  | All | 1 |  | 240 | 10 days | 1 | 1 | 1 | 1 | 4
| Architecture |  |  |  |  | 3 |  | 0 |  |  |  |  | 0
|  | Designing website layout | Requirements Analyst | All | 2 |  |  |  | 0 |  |  |  | 0
|  | Gather media |  |  | 1 |  |  |  | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
| Documentation |  |  |  |  | 10 |  | 2 |  |  |  |  | 0
|  | Project plan | Requirements Analyst | All | 1 |  |  |  | 0 |  |  |  | 0
|  | Milestone / iteration breakdown | Project Manager | All | 1 |  | 2 |  | 2 | 2 | 2 | 2 | 8
|  | Project documention |  | All | 2 | [7 empty] | 0
|  | Project report |  | All | 2 | [7 empty] | 0
|  | Testing report |  | All | 1 | [7 empty] | 0
|  | User and developer guides |  | All | 3 | [7 empty] | 0
Design & Build | [12 empty] | 0
Iteration 1: | Development |  |  |  |  | 24 |  | 0 |  |  |  |  | 0
|  | Determine technology needs. | Developer | All | 4 | [7 empty] | 0
|  | Research Wordpress environment. | Developer | All | 2 | [7 empty] | 0
|  | Research current website for existing problems and potential improvements | Developer | All | 1
|  | Fix font-family and font-size on different parts of the website (headers, paragraphs, etc). | Developer, UX Designer | Sandy Yang | 3 | [7 empty] | 0
|  | Update widget for "Contact Us". | Developer | Omer Khan | 1 | [7 empty] | 0
|  | Add captcha verification. | Developer | Ruby Rios | 1 | [7 empty] | 0
|  | Update theme: Color scheme, logo, headers, buttons, tabs, etc. to be consistent throughout website. | Developer, UX Designer | Ruby Rios | 5 | [7 empty] | 0
|  | Add appropriate contents for each page (Contact, About Company, History, etc). | Developer | Thomas Tran | 3 | [7 empty] | 0
|  | Delete, add, and edit existing pages on the site. Update directory and determine paths. | Developer | Omer Khan | 4 | [7 empty] | 0
| Testing |  |  |  |  | 2 |  | 0 |  |  |  |  | 0
|  | Testing current features of Website | Developer, Quality Assurance | All | 1
|  | Testing features of Wordpress (inventory, ecommerce, etc.) | Developer, Quality Assurance | All | 2 | [7 empty] | 0
Iteration 2: | [5 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
0
0
0
[6 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
0
0
0
[6 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
0
Iteration 3: | [5 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
0
0
[6 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
0
0
0
[6 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
Total |  |  |  |  | 44 | 43 | 28 | 246 | 7 | 7 | 7 | 7 | 28