## Iteration Estimated Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Omer Khan | Ruby Rios | Thomas Tran | Sandy Yang | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
[5 empty] | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Requirements |  |  |  |  | 4 |  | 244 |  |  |  |  | 20
|  | Research business | Requirements Analyst | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Gather information (questionnaire) | Requirements Analyst | All | 1 |  | 2 |  | 2 | 2 | 2 | 2 | 8
|  | Analyze business needs | Requirements Analyst | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Gain access to current website (Wordpress) |  | All | 1 |  | 240 | 10 days | 1 | 1 | 1 | 1 | 4
| Architecture |  |  |  |  | 3 |  | 2 |  |  |  |  | 8
|  | Designing website layout | Requirements Analyst | All | 2 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Gather media |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
| Documentation |  |  |  |  | 7 |  | 12 |  |  |  |  | 44
|  | Project plan | Requirements Analyst | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Milestone / iteration breakdown | Project Manager | All | 1 |  | 2 |  | 2 | 2 | 2 | 2 | 8
|  | Project documention | Requirements Analyst | All | 2 |  | 3 |  | 3 | 3 | 3 | 3 | 12
|  | Project report (requested by Client) | Requirements Analyst | All | 2 |  | 4 |  | 4 | 4 | 4 | 4 | 16
|  | Testing report | Quality Assurance | All | 1 |  | 2 |  | 1 | 1 | 1 | 1 | 4
Design & Build | [8 empty] | 18 | 18 | 18 | 18 | 72
Iteration 1: | Development |  |  |  |  | 24 |  | 26.5 |  |  |  |  | 73.9
|  | Determine technology needs. | Developer | All | 4 |  | 5 |  | 5 | 5 | 5 | 5 | 20
|  | Research Wordpress environment. | Developer | All | 2 |  | 3 |  | 3 | 3 | 3 | 3 | 12
|  | Research current website for existing problems and potential improvements | Developer | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Clean up current WordPress user database. Add “customer” and “wholesaler” roles. | Developer | Thomas Tran | 1 |  | 0.5 |  | 0 | 0 | 0.5 | 0 | 0.5
|  | Add and optimize inventory input. Figure out all possible parameters for columns. Create a key (Completed) Find an easier way to tie user roles to product prices (Still researching). | Developer | Sandy Yang and Thomas Tran | 8 |  | 7 |  | 0 | 0 | 2 | 7 | 9
|  | Add captcha verification. | Developer | Omer Khan | 2 |  | 3 |  | 2 | 0 | 0 | 0 | 2
|  | Plan to merge seasonal and promotional pages into the shop page (create additional wholesaler tier levels for more varying prices) | Developer | Thomas Tran | 2 |  | 2 |  | 0 | 0 | 2 | 0 | 2
|  | Update promo pages for wholesalers only. (Bulk-buying prices) | Developer | Thomas Tran | 2 |  | 2 |  | 0 | 0 | 2 | 0 | 2
|  | Link inventory to ecommerce. | Developer | Sandy Yang | 2 |  | 3 |  | 0 | 0 | 0 | 3 | 3
|  | SKU handling and altering product details. | Developer | Sandy Yang | 2 |  | 3 |  | 0 | 0 | 0 | 3 | 3
|  | Add checkout options for customers. Link payment (paypal etc) to the checkout. | Developer | Omer Khan | 1 |  | 3 |  | 3 | 0 | 0 | 0 | 3
|  | Add “cart abandonment” feature. | Developer | Omer Khan | 1 |  | 1 |  | 1 | 0 | 0 | 0 | 1
|  | Update Sitemap. |  | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Update Iteration Est. Effort Spreadsheet |  | All | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 8
|  | Submit files to canvas (Have everyone look everything over first). |  | All | 0.1 |  | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.4
| Testing |  |  |  |  | 2 |  | 3 |  |  |  |  | 12
|  | Testing current features of Website | Developer, Quality Assurance | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Testing features of Wordpress (inventory, ecommerce, etc.) | Developer, Quality Assurance | All | 2 |  | 3 |  | 2 | 1 | 2 | 3 | 8
[9 empty] | 39.1 | 32.1 | 39.6 | 47.1 | 157.9
Iteration 2: | Development |  |  |  |  | 16 |  | 13 |  |  |  |  | 19
|  | Create separate login pages for customers and wholesalers. | Developer | Sandy Yang | 2 |  | 3 |  | 0 | 0 | 0 | 3 | 3
|  | Incorporate “variable” products for import (documentation and import file). | Developer | Thomas Tran | 2 |  | 2 |  | 0 | 0 | 2 | 0 | 2
|  | Research current website for existing problems and potential improvements. | Developer | All | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 8
|  | Update sitemap. | UI/UX Designer | Outside Team | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Update widget for “Contact Us”. Add email subscription options for customers. | Developer | Omer Khan | 4 |  | 2 |  | 2 | 0 | 0 | 0 | 2
|  | Add customer and wholesale FAQ pages. | Developer | Sandy Yang | 2 |  | 2 |  | 0 | 0 | 0 | 2 | 2
|  | Associate different prices based on user roles (4 different roles). | Developer | Thomas Tran | 4 |  | 2 |  | 0 | 0 | 2 | 0 | 2
|  | Allow customers to rate and review products | Developer | Omer Khan | 2 |  | 1 |  | 1 | 0 | 0 | 0 | 1
[9 empty] | 44.1 | 34.1 | 45.6 | 54.1 | 177.9
Iteration 3: | Development |  |  |  |  | 38 |  | 0 |  |  |  |  | 0
|  | Create wholesale order tracking page. | Developer, UI/UX Designer | Sandy Yang | 2 | [7 empty] | 0
|  | Clean current and add new content and pages. | Developer, UI/UX Designer | Thomas Tran | 2 | [7 empty] | 0
|  | Clean website visuals (fonts, logos, etc) | Developer, UI/UX Designer | Omer Khan | 5 | [7 empty] | 0
|  | Add questions and answers to customer and wholesale FAQ pages. | Developer | Omer Khan | 5 | [7 empty] | 0
|  | Add and optimize inventory input. | Developer | Thomas Tran | 5 | [7 empty] | 0
|  | Update sitemap. | UI/UX Designer | Outside Team | [8 empty] | 0
|  | Possibly create a drop down menu for wholesale ->login ->faq. | UI/UX Designer | Sandy Yang | 1 | [7 empty] | 0
|  | Update and publish wholesale and consumer log in pages. | Developer | Ruby Rios | 1 | [7 empty] | 0
|  | Add manual approval for wholesale accounts with notification. | Developer | Ruby Rios | 2 | [7 empty] | 0
|  | Create import file(s) for all inventory based on categories. Import all product inventory. | Developer | Thomas Tran | 5
|  | Implement tax tables for consumers only. | Developer | Sandy Yang | 3 | [7 empty] | 0
|  | Update widget for “Contact Us”. Add email subscription options for customers. | Developer | Omer Khan | 2
|  | Allow customers to rate and review products | Developer | Omer Khan | 2
|  | Research shipping and order tracking plugins. | Developer | Sandy Yang | 3 | [7 empty] | 0
| Testing |  |  |  |  | 6 |  | 0 |  |  |  |  | 0
|  | Step through website as various users to ensure a seamless and intuitive experience | Developer, Quality Assurance | All | 3 | [7 empty] | 0
|  | Test customer and wholesale login to ensure it is working. | Developer, Quality Assurance | All | 2 | [7 empty] | 0
|  | Test shopping oriented pages for various users. | Developer, Quality Assurance | All | 1 | [7 empty] | 0
| Post Development |  |  |  |  | 7 |  | 0 |  |  |  |  | 0
|  | Create user/developer guides | Project Manager | All | 3 | [7 empty] | 0
|  | Complete any additional work from the clients to ensure website is up to their standards | Developer, Quality Assurance | All | 4 | [7 empty] | 0
Total |  |  |  |  | 117.1 | 107 | 177.9 | 300.5 | 44.1 | 34.1 | 45.6 | 54.1 | 177.9