## Iteration Estimated Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Omer Khan | Ruby Rios | Thomas Tran | Sandy Yang | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
[5 empty] | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Requirements |  |  |  |  | 4 |  | 244 |  |  |  |  | 20
|  | Research business | Requirements Analyst | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Gather information (questionnaire) | Requirements Analyst | All | 1 |  | 2 |  | 2 | 2 | 2 | 2 | 8
|  | Analyze business needs | Requirements Analyst | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Gain access to current website (Wordpress) |  | All | 1 |  | 240 | 10 days | 1 | 1 | 1 | 1 | 4
| Architecture |  |  |  |  | 3 |  | 2 |  |  |  |  | 8
|  | Designing website layout | Requirements Analyst | All | 2 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Gather media |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
| Documentation |  |  |  |  | 7 |  | 12 |  |  |  |  | 44
|  | Project plan | Requirements Analyst | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Milestone / iteration breakdown | Project Manager | All | 1 |  | 2 |  | 2 | 2 | 2 | 2 | 8
|  | Project documention | Requirements Analyst | All | 2 |  | 3 |  | 3 | 3 | 3 | 3 | 12
|  | Project report (requested by Client) | Requirements Analyst | All | 2 |  | 4 |  | 4 | 4 | 4 | 4 | 16
|  | Testing report | Quality Assurance | All | 1 |  | 2 |  | 1 | 1 | 1 | 1 | 4
Design & Build | [8 empty] | 18 | 18 | 18 | 18 | 72
Iteration 1: | Development |  |  |  |  | 24 |  | 26.5 |  |  |  |  | 73.9
|  | Determine technology needs. | Developer | All | 4 |  | 5 |  | 5 | 5 | 5 | 5 | 20
|  | Research Wordpress environment. | Developer | All | 2 |  | 3 |  | 3 | 3 | 3 | 3 | 12
|  | Research current website for existing problems and potential improvements | Developer | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Clean up current WordPress user database. Add “customer” and “wholesaler” roles. | Developer | Thomas Tran | 1 |  | 0.5 |  | 0 | 0 | 0.5 | 0 | 0.5
|  | Add and optimize inventory input. Figure out all possible parameters for columns. Create a key (Completed) Find an easier way to tie user roles to product prices (Still researching). | Developer | Sandy Yang and Thomas Tran | 8 |  | 7 |  | 0 | 0 | 2 | 7 | 9
|  | Add captcha verification. | Developer | Omer Khan | 2 |  | 3 |  | 2 | 0 | 0 | 0 | 2
|  | Plan to merge seasonal and promotional pages into the shop page (create additional wholesaler tier levels for more varying prices) | Developer | Thomas Tran | 2 |  | 2 |  | 0 | 0 | 2 | 0 | 2
|  | Update promo pages for wholesalers only. (Bulk-buying prices) | Developer | Thomas Tran | 2 |  | 2 |  | 0 | 0 | 2 | 0 | 2
|  | Link inventory to ecommerce. | Developer | Sandy Yang | 2 |  | 3 |  | 0 | 0 | 0 | 3 | 3
|  | SKU handling and altering product details. | Developer | Sandy Yang | 2 |  | 3 |  | 0 | 0 | 0 | 3 | 3
|  | Add checkout options for customers. Link payment (paypal etc) to the checkout. | Developer | Omer Khan | 1 |  | 3 |  | 3 | 0 | 0 | 0 | 3
|  | Add “cart abandonment” feature. | Developer | Omer Khan | 1 |  | 1 |  | 1 | 0 | 0 | 0 | 1
|  | Update Sitemap. |  | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Update Iteration Est. Effort Spreadsheet |  | All | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 8
|  | Submit files to canvas (Have everyone look everything over first). |  | All | 0.1 |  | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.4
| Testing |  |  |  |  | 2 |  | 3 |  |  |  |  | 12
|  | Testing current features of Website | Developer, Quality Assurance | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Testing features of Wordpress (inventory, ecommerce, etc.) | Developer, Quality Assurance | All | 2 |  | 3 |  | 2 | 1 | 2 | 3 | 8
[9 empty] | 39.1 | 32.1 | 39.6 | 47.1 | 157.9
Iteration 2: | Development |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
0
0
0
0
0
0
| Testing |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
0
0
0
0
0
[6 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
0
[9 empty] | 39.1 | 32.1 | 39.6 | 47.1 | 157.9
Iteration 3: | Development |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
0
0
0
0
0
0
| Testing |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
0
0
0
0
0
[6 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
Total |  |  |  |  | 48.1 | 40 | 157.9 | 287.5 | 39.1 | 32.1 | 39.6 | 47.1 | 157.9